## Sheet1
SMCC Plan of Action 2018-2019
This Plan of action (PoA) is the translation into activities of the three priorities of the Strengthening Movement Coordination and Cooperation (SMCC) process for the period 2017-2019 which have been presented and endorsed through Resolution 1 at the Council of Delegates 2017 (CoD17) as follows: 1. increase literacy in and the use of the Movement’s coordination tools and mechanisms and contribute to mindset change 2. improve the cost-effective and operationally relevant provision of “services and support” in high-interest areas where the Movement can assert its know-how and demonstrate its added-value 3. continue building on successful examples of joint resource mobilization More concretely this PoA derives from the CoD17 also tasking "the ICRC and the International Federation, with active engagement and contributions from National Societies, to oversee the implementation of recommendations and to report back to the 2019 Council of Delegates on the progress made."
Priority 1: Continue to increase SMCC literacy in and the use of the Movement's coordination tools and mechanisms and contribute to mindset change
Objective | Activities | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | Technical Team | Indicators/deliverables | Required Resources
1.1 Improve SMCC mindset and ensure continuous operational integration through a more systematic dissemination of best practices and improved guidance to practitioners | 1.1.1 Replicate SMCC contexts of focus in each Regions with peer support from the 5 initial country labs | [20 empty] | SMCC Coordination Group | 1. % of new contexts where SMCC brings demonstrable added value | > NS from country labs to work as peers in each of the Regions > Other NS to provide possible technical and financial (travel, etc) support to each lab peers for the "replication" work | bar: A to N
| 1.1.2 Update, maintain, promote and ensure easy access to the online coordination toolkit used for promotion and training on the SMCC framework and tools available | [20 empty] | SMCC Coordination Group | 1. Results of online survey on user-friendliness of the tool-kit 2. # connexions to the website | > One or several NS to (co-)host the micro-website, to provide technical and financial support for the development of the toolkit as well as the long term maintenance of the site | bar: A to N
| 1.1.3 Continue influencing/guiding Operations' decision-makers so that SMCC spirit and tools are applied in all new emergencies and in normal situations, notably through the presence of technical support teams comprising HNS, PNS, IFRC and ICRC at the regional level | [20 empty] | SMCC Coordination Group | 1. # of interventions or participation to trainings from Regional teams 2. % of emergencies seeing efficient coordination as per SMCC guidance 3. # of non-emergency contexts where SMCC elements have been used | > NS willing to represent their peers in the technical support teams at the regional level to promote use of SMCC standards and tools in all contexts and to ensure adequate integration in trainings and seminars. > Note that one seat shall be allocated to the Country Lab NS | bar: A to N
| 1.1.4 Raise SMCC awareness at the level of senior decision-makers across the Movement through specific meetings and ad hoc briefings | [20 empty] | SMCC Coordination Group | 1. # of sessions held | bar: A to N
| 1.1.5 Update and disseminate the revised Movement regulatory framework presentation | [20 empty] | SMCC Coordination Group | 1. Presentation available 2. # of times used 3. # of people reached | > NS with strong legal team to support the production of a revised presentation and its future promotion | bar: A to N
1.2 Increase the overall SMCC awareness through an SMCC Training catalogue and systematic inclusion in relevant trainings | 1.2.1 Produce a limited number of short information videos – Including testimonies from high level representatives & practitioners and video animation | [20 empty] | JF Goulay Darko Jordanov | 1. # of people trained/reached | > NS partner with specific technical skills to support draft scripts, produce and disseminate the products, and possibly support the process financially | bar: M to S
| 1.2.2 Develop an Online Certification Curriculum, including Online Course and Online Self-Assessment | [20 empty] | Darko Jordanov JF Goulay | 1. # of people certified 2. First certifications by CoD 2019 | > Consultant/company to produce the online course to an approximate cost of around 50,000 CHF (including translations). > NS is/are welcomed to support financial or event take the lead on this process, including the production phase, while the content will be defined by jointly with the international components. | bar: M to J
| 1.2.3 Further include SMCC framework and coordination mechanisms in IMPACT courses and ICRC/IFRC regular staff meeting sessions on site | [20 empty] | JF Goulay Darko Jordanov | 1. # of people trained | bar: O to N; F to M
| 1.2.4 Include SMCC modules (based in the online toolkit) in internal trainings, briefings and development seminars of international staff of all Movement components | [20 empty] | SMCC Coordination team | 1. Results of online survey with Movement personnel deployed internationally 2. # of components having conducted internal trainings | > NS to support in designing, running and analysing a survey for Movement field practitioners | bar: J to M
1.3 Further disseminate and refine Movement coordination tools and mechanisms across operational contexts | 1.3.1 Promote the use of MCAs and Movement Country Plans in all contexts where several partners are present and ensure effective setting up of the coordination mechanisms as well as the use of Mini-summit at the onset of emergencies | [20 empty] | SMCC Coordination Group | 1. # of contexts where MCA are established 2. # of contexts where Country Plans are implemented | > NS to participate in refining the concept, design and implementation of Movement country plans (online community of practice) | bar: A to N
| 1.3.2 Continue developing Movement contingency plans and maintaining them in emergency-prone contexts while capturing and sharing best practices across the Movement | [20 empty] | SMCC Coordination Group | 1. # of contexts where Mvt Contingency Plans are implemented | > Leadership at all level supported by regional SMCC teams to support and promote use of Movement contingency plans in each Regions | bar: A to N
Priority 2: Improve the cost-effective and operationally relevant provision of 'services and support' in high-interest areas
Objective | Activities | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | Responsibility | Indicators/deliverables | Required Resources
2.1 Further develop interoperability in logistics systems between Movement components | 2.1.1 Stocks: Strategic stock pre-positioning is otpimised across the Movement and cost-benefits are measured | [20 empty] | Christophe Hambye Thierry Balloy | 1. Number of interchangeable emergency response items. 2. Number of shared storage sites worldwide. 3. Value of joint pre-positioned stock. 4. Estimated saving like-for-like on storage costs (value/%). | > NSs part of the Logistics network to support the process and be sollicited depending on evolution | bar: S to D
| 2.1.2 Cash Transfer Programming: Logistics component of Cash Transfer Programs is aligned along all Movement partners, common standards and tools are defined and a shared pool of experts is established with a common competency framework | [20 empty] | Thierry Balloy Christophe Hambye | 1. Guidelines/SOPs are updated and common. 2. Tools are updated and common. 3. Trainings are updated and common. 4. Shared competency framework is agreed upon. 5. Pool management system is in place and first members identified. | > Head of project at IFRC, 04-12/2018 funded by SwissRC and BritishRC. For same or other NS to cover costs for 2019 | bar: M to M
| 2.1.3 Logistics Development: National Societies Logistics Development Standards and tools are updated and shared across the Movement | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | c | t | n | d | Christophe Hambye Thierry Balloy | 1. Necessary basic Logistics competencies are commonly defined. 2. Minimum standards of Movement-wide logistics are agreed upon. 3. Assesment tools are updated and common. 4. Trainings and development tools are updated and common. 5. A proposal is made on possible Movement-wide Logistics IT solution. | > NSs part of the Logistics network to support the process and be sollicited as and when required
| 2.1.4 Procurement: Sourcing Strategies for agreed categories are defined and used commonly | [20 empty] | Thierry Balloy Christophe Hambye | 1. Number of commonly agreed categories to source commonly. 2. # and estimated yearly value of common sourcing. 3. # and estimated yearly value of common LTA's | > NSs part of the Logistics network to support the process and be sollicited as and when required | bar: X to X
| 2.1.5 Fleet management: Fleet management tools and practices are shared across the Movement where possible, exploring options such as: common standards, stock optimisation, software compatibility or collaboration in training. | [20 empty] | Christophe Hambye Thierry Balloy | 1. Number of commonly agreed vehicles standards. 2. Number of fleet units exchanged 3. Number of shared Fleet Management Software/s 4. Number of shared trainings. | > NSs part of the Logistics network to support the process and be sollicited as and when required | bar: X to X
| 2.1.6 “Red Log”: SoPs are developed based on lessons learnt from past experiences and a "Red Log" concept is articulated with focus on common Tools and Procedures for shared Logistics Resources in major crisis. |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | c | t | n | d | Thierry Balloy Christophe Hambye | 1. ToR’s for the study are drafted. 2. Study is concluded. 3. Draft SoP’s for Red Log Response are available and in agreement within the Task Force 4. Model is piloted in one operation by 2019 5. Lessons Learns from the pilot are collected and gathered for further improvements. 6. Final SoP’s are made available by 2020. | > 3 to 5 NS to be part of the Task force to contribute to and pilot the model. > NS to provide a Head of Project for 6 months or to fund a consultant?
2.2 Further strenghen, streamline and harmonize safety and security management within the Movement | 2.2.1 Clarify security management agreements and field arrangements to the greatest extent possible as per current efforts in several operational contexts |  |  | X | [17 empty] | Karl Julisson Ali Naraghi | 1. Joint IFRC/ICRC Paper on Movement security arrangements | bar: X to X
| 2.2.2 Streamline security management tools and training for staff deployed internationally, in line with recommendations from the Security Focal Points Network working groups, notably identification of good practices |  |  | X | [17 empty] | Ali Naraghi Karl Julisson | 1. Set of good practices identified and made available (online plateform, etc.) 2. Extent to which terminology, definitions, templates, and process are streamlined in terms of tools and training material 3. Guidance for RCRC Security training curriculum is available | bar: X to X
| 2.2.3 Contribute to strenghening capacity-building support in safety and security management for NS and enhance NSs' self awareness of internal security management capacity | [20 empty] | Karl Julisson Ali Naraghi | 1. # of good practice disseminated 2. Updated IFRC 'Stay safe' training material. New ICRC 'Staying Alive' guidelines (incl. complementarity between the two documents). 3. # tools available in support to SAF Elements 1 and 8 4. IFRC to develop Good Security Management Practice guidelines for NS, aligned with the security attributes currently integrated in IFRC OCAC | bar: X to c
| 2.2.4 Increase the number of National Societies involved in security management through engagement with the Movement Security Focal Points Network and through alternate consultation forum with other NS |  |  | X | [17 empty] | Ali Naraghi Karl Julisson | 1. # of NS contributions to security management-related Movement-wide discussions | > NS to support external resource person for minimum time period of 12 months, with strong Movement experience to map contacts within NS, identify options to engage NS and present concrete recommendations to the Security Forum | bar: X to c
2.3 Further increase interoperability of surge capacities between Movement components | 2.3.1 Adapt and expand ERU Technical Working Groups to Movement-wide Technical Working Groups for surge |  | X | X | [17 empty] | Daniel Bolanos/ Susanne Amsler (+DMWG organising committee) | 1. Select relevant Technical Working Groups together with the technical departments of the concerned Movement component. | > NS part of the Technical Working Groups to support the process | bar: X to X
| 2.3.2 Explore alignement of competency frameworks for surge personnel across the Movement |  | X | X | [17 empty] | Daniel Bolanos/Susanne Amsler (+DMWG organising committee) | 1. Select 2 to 3 surge role profiles to pilote alignment in regards with both concerned competency frameworks. | > Managed through Reference Group 2, Surge Optimisation Process | bar: X to X
| 2.3.3 Enhance Movement-wide alignment and harmonization of surge training courses | [20 empty] | Daniel Bolanos/Susanne Amsler (+DMWG organising committee) | 1. Map of Movement-wide all surge training courses/modules. 2. Ensure adequate inclusion of SMCC and the different surge mechanisms and tools in all surge training courses/modules. | > NS to second external consultant with adequate technical skills > Managed through Reference Group 7 Surge Optimisation Process | bar: X to n
| 2.3.4 Explore and establish mechanisms to increase Movement-wide mobility of surge personnel |  | X | X | [17 empty] | Daniel Bolanos/Susanne Amsler (+DMWG organising committee) | 1. SOP for all surge mechanisms are available on how to deploy staff members from other Movement components. | > NS part of the technicl Working Groups to support the process | bar: X to X
| 2.3.5 Learn from the deployment of Movement Coordination Officers and ensure that the practice is adapted accordingly |  | X | X | [17 empty] | SMCC Coordination Group | 1. ToR and administrative procedures for the Movement Coordination Officer (MCO) are available.. 2. SOPs for deployments are defined | > NS to propose MCO candidates and to act as sponsoring partners, covering for possible deployments | bar: X to n
Priority 3: Continue building on successful examples of joint resource mobilisation
Objective | Activities | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | Responsibility | Indicators/deliverables | Required Resources
3.1 Continue improving coherence in resource mobilisation and developing modalities that ensure cost-efficiency and crediblity of the Movement response | 3.1.1 Learn from the implementation of the of the One International Appeal modality and adapt the practice and process on the basis of the results of an independent evaluation | [20 empty] | SMCC Coordination Group | 1. Evaluation report 2. # of partners made aware of evaluation results | > For NS to be part of the monitoring committee > Possible financial contribution from NS to the evaluation | bar: A to J
| 3.1.2 Develop new action points based on Management decision following evaluation of the One International Appeal and ensure implementation | [20 empty] | Ivana Mrdja Adib Nahas | 1. New action points integrated in PoA 2. Implementation rate of new action points | > Depending on new directions, NS will be called to support the implementation and future developments | bar: A to N
| 3.1.3 Disseminate SOPs for One International Appeal and create Q&A to go with it | [20 empty] | Katy Attfield Pascale Meige | 1. SOPs and Q&A avaialble 2. % of new 1IA where SOPs have been used | bar: A to D
| 3.1.4 Develop SOPs for Coordinated Appeals in line with the ones for 1IA and ensure their dissemination | [20 empty] | Pascale Meige Katy Attfield | 1. SOPS available 2. % of new Coordinated Appeals where SOPs have been used | bar: M to J